## Project Execution Timeline
PROJECT BRIEF / DESCRIPTION | BUILDING / LOCATION2 | PHYSICAL WORKS START | PROJECT FINISH DATE | COMMENTS
Toilet & Shower upgrade - Phase 2 | B112-115 | 2024 | 2025-02-27 | Completed
Water main resilience | Mt. Albert | 2025-07-01 | 2025-12-25 | Dates Estimated
Repair/ replacement of roof | B115 | 2025-11-01 | 2026-07-01
Earthquake strengthening | B48 | 2025-07-04 | 2026-02-28
Replacement Blinds | B48 | 2025-10-01 | 2025-12-12
Paths and walkways | Mt. Albert | 2025-08-15 | 2025-10-15
Walkway canopies | Mt. Albert | 2025-08-01 | 2025-12-12
112 generator replacement | B112 |  |  | Completed
113 generator replacement | B113 |  |  | Completed
Indoor furniture refurb student spaces | Mt. Albert | 2025-04-07 | 2025-11-30
Outdoor furniture for student spaces | Mt. Albert | 2025-04-07 | 2025-11-30
Garden re-landscaping | Mt. Albert | 2025-04-01 | 2025-06-30
Campus signage | Campus | 2025-03-24 | 2025-10-31
Building Signs 111-115 internal | B111-115 | 2025-03-06 | 2025-09-30
Building number sign | Mt. Albert | 2025-03-24 | 2025-10-31
Fleet vehicles and shuttle us graphic update | Mt. Albert | 2025-02-18 | 2025-04-30
Gate 4 LED Billboard | Mt. Albert | 2025-07-01 | 31/04/2025
Gate 4 - new entrance & gates to Unitec | Mt. Albert | 2024-07-01 | 31/04/2025
Road upgrade and line marking | Mt. Albert | 2025-07-01 | 2025-09-21
Mt Albert HVAC upgrade | Mt. Albert | 2025-08-01 | 2025-09-01
Waitakere HVAC | B510 | 2025-09-01 | 2025-12-01
Old fire Panel Upgrade | B107-97 | 2025-09-01 | 2025-09-30
Automatic doors | B110 / B180 | 2025-03-15 | 2025-05-01 | Completed
BMS upgrade | BMS | 2025-06-15 | 2025-10-31
Car park and external lights | Mt. Albert | 2025-08-01 | 2025-09-30
MTA Lift replacement | B510 | 2025-06-01 | 2025-08-20
Waitakere carpark security - equipment | Waitakere | 2025-06-01 | 2025-08-01
Unitec access control upgrade | Mt. Albert | 2025-07-01 | Completed
B111 entrance canopy upgrade | B111 | 2025-07-02 | 2025-08-15 | Completed
security fencing | Mt. Albert | 2025-06-01 | 2025-07-01
LED light upgrade | Mt. Albert | 2025-07-01 | 2025-10-28
Water meter project | Mt. Albert | 2025-06-01 | 2025-11-01
Ford Transit shuttle - (excl GST) | Mt. Albert | 2025-02-17 | 2025-03-17 | Completed
Campus storage | Mt. Albert | 2025-03-17 | 2025-04-01
Creative industry Dance studio/phase 2 | B108 | 2025-06-30 | 2025-10-21
B171 Block2 Upgrade | B171 | 2025-08-19 | 2025-12-09
Waitakere Kitchen upgrades 500 + 510 | Waitakere | 2025-11-01 | 2025-12-01
108 toilet sink and tops replacement | B108 | 2025-10-01 | 2025-12-01
Waitakere library carpets ( Remaining rooms) | B520 | 2025-10-01 | 2025-12-12
Underground services (water meters and SV) | Mt. Albert | 2025-07-01 | 2025-11-28
B180 Stairway door | B180 |  |  | Completed
Long black Chiller Cabinet replaement | B180
Alterations / relocation of Tyre and 3phase drills in B307 | B307 | 2025-02-13 | 2025-04-20
Lighting upgrade to LED with controls | B111-115 | 2025-08-01 | 2025-12-12
Painting corridors and lecture rooms | B111-115 | 2025-09-01 | 2025-12-12
Window blinds | B111-115 | 2025-06-30 | 2025-07-21
Replace key lock to Access control | B111-115 | 2025-08-01 | 2025-09-01
Air-con / HVAC upgrade, connect to BMS | B111-115 | 2025-05-01 | 2025-11-01
Carpets in various office and lecture rooms | B111-115 | 2025-09-22 | 2025-12-12
Internal signage | B111-115 | 2025-08-01 | 2025-12-12
Fire Panel upgrade (B112 only) | B111-115 |  |  | Completed
Waitakere Student Central Blinds and Building Corner graphic | B500 | 2025-03-30 | 2025-05-31
Note on A20: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Check with Bill if required this year
Note on A25: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: New fitting B111-115
Note on A32: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: B111-115
Note on A35: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Vehicle branding/signage